## Projects Timeline
Averna LATM Tester Projects Timeline
No | Main activities | Response by | 1st Week | 2nd Week | 3rd Week | 4th Week | 5th Week
1 | Design the LATM controller board diagram showing the wiring connections needed to replace the JRK controller on the Averna testers. | Apicha
2 | Order LATM controller board, Prog Test Board, position-sensor flex cable, position sensor adapter interposer circuit board, 51-conductor flex cable, and EL Motor interposer cable. (Not sure for lead time of these materials) | Apicha/LMN
3 | Software Development (TestStand, LabView, Supernova) | Apicha/FBN
4 | Uninstall the JRK controller on one of Averna testers and replace with it the LATM control board. | Apicha/FBN
5 | Wiring and verifying the LATM control board with the LATM unit manually. | Apicha/FBN
6 | Sofware and Hardware Validation with LATM units. | Apicha/FBN
7 | Uninstall the JRK controller on 2nd of Averna testers and replace with it the LATM control board. | Apicha/FBN
8 | Wiring and verifying the LATM control board with the LATM unit manually. | Apicha/FBN
9 | Sofware and Hardware Validation | Apicha/FBN
10 | Doing GR&R on both LATM test stations | Apicha/FBN
11 | Training FBN Engineers/operators how to test the LATM units with new LATM test stations. | Apicha
Plan
Done